## Sheet2
# |  | Tasks | Hours
1 | Installation on Server
| 1.1 | Customize web config | 0.5
| 1.2 | SQL scripts to update existing Database | 1
| 1.3 | Move dll's and files | 1.5
| 1.4 | Testing | 1
2 | Kiosk Login (New Member)
| 2.1 | Exisiting member type check to be included during login | 1
| 2.2 | UI changes depending on member type selected. | 5
| 2.3 | Writing and reading information from database. | 5
| 2.4 | Testing | 1
3 | Kiosk Login (Exisiting Member)
| 3.1 | Existing member Check on login to allow member type update | 1
| 3.2 | UI changes for exisiting member to input information depending upon the member type selected. | 5
| 3.3 | Writing and reading information from database. | 5
| 3.4 | Testing | 1
4 | Kiosk Login (ALL or TFME member type)
| 4.1 | Existing member Check on login to allow member type update to CSS or MEM | 0.5
| 4.2 | Link to CSS/ MEM membership page and Clearing out ALL/ TFME membership information | 2
| 4.3 | Testing | 1
5 | Check to stop User
| 5.1 | Check Name_demo.REG_HOLD on login in | 0.5
| 5.2 | Page to display test to "See Susan" | 0.75
| 5.3 | If user already registered check | 0.75
| 5.4 | Testing | 1
|  | Total Programming Hours: | 34.5